## Project_Charter_
PROJECT CHARTER	Rev.01 26.10.2024
GENERAL PROJECT INFORMATION
PROJECT TITLE	Formulation Fill Finish Process Optimization
PROJECT MANAGER	Martin Brown	Martin.Brown@Chokpharm.ie
PROJECT SPONSOR	John Woods	John.Woods@Chokpharm.ie
BLACK BELTS ASSIGNED	James Moonan	James.Moonan@Chokpharm.ie
GREEN BELTS ASSIGNED	Ivana Benisek Celic	Ivana.BeniskCelic@Chokpharm.ie
	Justyna skiba	Justyna.Skiba@Chokpharm.ie
	Ronald Kayinga	Ronald.Kayinga@Chokpharm.ie
PROJECT OVERWIEV
Business Impact	Increased Costs: Extra shifts and non-conformance rework increase operational costs. / Supply Chain Disruptions: Delayed production and quality issues impact supply chain reliability. / Customer Satisfaction: Potential delays in product delivery and quality concerns can negatively impact customer satisfaction.	Problem/Opportunity Statement:
Links to Strategic Objectives	Improve overall equipment effectiveness (OEE) / Reduce cycle time and lead time / Enhance product quality and reduce non-conformances	The current formulation fill finish process suffers from excessive turnaround times and a high rate of non-conformances, leading to increased costs, supply chain disruptions and potential quality risks.
		Definition of Done:
Benefits/Achievements and Benefit Types	Hard Benefits: / Reduced production costs / Increased production output / Improved on-time delivery / Soft Benefits: / Improved employee morale / Strengthened quality culture Enhanced process efficiency and effectiveness Improved brand perception	Reduced turnaround time for dispensing and testing by 20% / Non-conformance rate reduced by 50% / Standardized work instructions and training materials developed and implemented / Sustained process improvements through implemented control plan
		EXPECTED START DATE		EXPECTED COMPLETION DATE
		26/10/2024		21/05/2025
Efforts	Process mapping and analysis / Identify and eliminate bottlenecks / Implement lean and Six Sigma methodologies / Optimize equipment and resource utilization / Improve quality control procedures / Develop and implement a robust change management plan	EXPECTED SAVINGS		ESTIMATED COSTS
Key Metrics/Goals	SMART Goal: Reduce turnaround time for dispensing and testing by 20% within 3 months. / Y=f(x): Turnaround Time = f(Equipment Efficiency, Process Optimization, Operator Skill)	,,,,,		,,,,,,
PROJECT SCOPE
Within scope	Formulation and fill finish process / Raw material dispensing and testing / Equipment and resource utilization / Quality control procedures / Operator training and skill development
Outside of scope	Upstream and downstream processes / Regulatory compliance (outside the scope of this project) / Major equipment procurement and installation
PROJECT PLAN
KEY MILESTONE		START		FINISH
Form Project Team / Preliminary Review / Scope		26/10/2024		26/10/2024
Finalize Project Plan / Charter / Kick Off		,,,,		,,,,
Define Phase
Measurement Phase
Analysis Phase
Improvement Phase
Control Phase
Project Summary Report and Close Out
RISK ASSESMENT
RISK1	Equipment failure or breakdown
RISK2	Supplier delays or quality issues
RISK3	Operator errors or lack of training
RISK4	Regulatory changes or audits
TEAM SELECTION AND MEMBERS
CORE TEAM
Project Manager	Oversees the project, leads the team, and ensures project objectives are met.
Process Engineer	Analyses the current process, identifies bottlenecks, and proposes process improvements.
Quality Assurance Engineer	Ensures product quality and compliance with regulatory requirements
Validation Engineer	Develops and executes validation protocols to ensure process and equipment performance
Operations Supervisor	Provides input on operational challenges and opportunities for improvement.
EXTENDED TEAM
Equipment Technicians	Support equipment maintenance and repairs
Operators	Provide insights into daily operations and potential issues
Supply Chain Manager	Coordinates the procurement of raw materials and the distribution of finished products
Regulatory Affairs Specialist	Ensures compliance with regulatory requirements
Finance Manager	Provides financial analysis and cost-benefit assessments
DEFINITOPN OF TERMS
Turnaround time: Time taken to complete a specific task or process / Non-conformance: Deviation from specified requirements / OEE: Overall Equipment Effectiveness
APPROVALS
Project Manager	Project Sponsor	Black Belt		Green Belts

## SIPOC
SUPPLIERS			INPUTS			PROCESSES				OUTPUTS			CUSTOMERS